Sample Development Appraisal

FOR BORROWERS

Contents

3 - Requirement

4, 5 – Case Overview

6, 7 – Developer Profile

8 - Development Appraisal

9 - Schedule

10 - Planning

11 - Professional Team

12 - Comparable Properties

13 - Assets and Liabilities

14 – Further supporting information

15, 16 – Appendix

Requirement (for lenders)

An 18-month facility of £2,275,000 is sought to enable Globe Results Limited to acquire a site in 10 Kings Road, York, YO1 1ET and undertake the development of 4 new houses with a total of 6000 sq ft.

The loan represents 65% of GDV and 90% of costs.

There will be cash equity of £266,200 in the transaction.

Detailed planning in place at the time of completion.

The build will be undertaken by the developer using sub-contractors known to the developer with an expected budget of £1,175,000 or £195.83 per sq ft (including professional fees).

Repayment will come from sale of units.

(Lender) support will represent 65% of the projected £3.5m GDV

(Lender) support will represent 90% of costs

Case Overview

Ownership

How will you own the new development?

UK Limited Company

Has the company or pension been formed yet?

Yes

What is the Name of the UK Limited Company?

Globe Results Limited

UK Limited Company Number

12322370

Site Details

Address

10 Kings Road, York, YO1 1ET

Will you have planning permission before or on completion of this loan?

Detailed Planning

Do you own the property?

No

Purchase process

Regular Purchase

Planning

Who was responsible for gaining the planning?

Borrower

Please provide any futher information on the planning permission & process

We purchased the site with outline planning 6 months ago, with a bridging loan. We have now dealt with all reserved matters, and have detailed planning permission for 26x 3 & 4 bed houses.

Tell us about how the site will look when the loan completes?

The site will be bare land at completion.

Build procurement

Please tell us about your build procurement

Self-managed procurement (borrowers will manage the individual trade packages)

Please provide us with more information about your chosen procurement method?

We are managing the build ourselves and will tender the individual packages. We have worked this way on 3x previous personal projects. Prior to that one of our shareholders worked as a PM for 10 years at a regional house builder, managing projects of up to 150 houses.

Deposit source

Please tell us what percentage of the total deposit is planned to come directly from the borrowers / named shareholders and how that money is being raised?

50% of the deposit will come from the shareholders and 50% will come from investors. The investors are family and friends and their investment will be secured as a 2nd charge.

Exit strategy

How do you plan to repay the development loan?

Part Sale & Part-Refinance

Completion

Do you have a set completion date for the initial loan?

Yes

Confirmed completion date

02-05-2022

Mezzanine

If mezzanine finance is available for your project, would you like to get quotes?

No

Preferences

Biggest loan	Yes - 1

Best pricing	Yes - 2

Speed of completion	Yes - 4

Great customer service	Yes - 3

Existing relationships

Please list the names of any lenders below that you do not wish to be approached to fund this project.

Paragon Bank

Further information

Is there anything else you wish to disclose at this time, positive or negative, that a lender should know before they bid on your project?

No

Shareholders

John Doe

Email Address: john@doe.com

Ownership Percentage: 100%

Developer Profile

How will you own the new development?

UK Limited Company

Are there any lenders that you don't want Brickflow to talk to?

Paragon Bank

Has the company or pension been formed yet?

Yes

Company, pension or partnership name: Globe Results Limited

Company or partnership number: 12322370

Partner Information

Number of partners: 1

Name: John Doe

Email Address: john@doe.com

Date of Birth: 1975-09-02

National Insurance No.   WK734588A

Ownership Percentage: 100%

Address: 32 Brookside Road, Istead Rise, Gravesend DA13 9JJ

Years at this address :  2

If less than 3 years , previous address:-

3 Farley Road, Gravesend DA12 2LT

Has the Applicant Developed Property Before? Yes

Shareholder Experience: John Doe

| How Many Years has John been a Developer? | 15 |
| --- | --- |
| Number of Developments John has Completed as an Owner | 7 |
| Number of Residential Projects | 7 |
| Number of Commercial Projects | 0 |
| Years of Experience as an Architect | 0 |
| Years of Experience as a Builder | 0 |
| Years of Experience as a Carpenter | 0 |
| Years of Experience as an Electrician | 0 |
| Years of Experience as an Estate Agency | 0 |
| Years of Experience as a Planner | 0 |
| Years of Experience as a Project Manager | 10 |
| Years of Experience as a Property Surveyor | 0 |
| Years of Experience as a Quantity Surveyor | 0 |
| Years of Experience as a Structural Engineer | 0 |
| Skills | - |
| Professional Qualifications | BA / BSc |

Developer Profile continued: Previous Developments

| Development 1 |  |
| --- | --- |
| Were you One of the Owners or an Employee? | Owner |
| Development Type | None |
| Address Line 1 | 32 Brookside Road |
| Address Line 2 | Istead Rise |
| Address Line 3 | Gravesend |
| Address Line 4 | Kent |
| Postcode | DA13 9JJ |
| Acquisition Date | 2016-09-30 |
| Acquisition Costs | £350,000.00 |
| Did you use Developer Finance? | Yes |
| Development Finance Lender Name | Masthaven |
| Area Unit | Square Feet |
| Gross Internal Area sq.m | 3000 |
| Build Costs | £350,000.00 |
| Project Time in Months | 12 |
| GDV | £900,000.00 |
| Sold on Exit | No |
| Description of Works | Knock down and rebuild of main residence |

| Development 2 |  |
| --- | --- |
| Were you One of the Owners or an Employee? | Owner |
| Development Type | None |
| Address Line 1 | 7 Soho Square |
| Address Line 3 | London |
| Postcode | W1D 3QB |
| Acquisition Date | 2018-02-01 |
| Acquisition Costs | £3,500,000.00 |
| Did you use Developer Finance? | Yes |
| Development Finance Lender Name | Paragon |
| Area Unit | Square Meters |
| Gross Internal Area sq.m | 4500 |
| Build Costs | £9,000,000.00 |
| Project Time in Months | 24 |
| GDV | £18,000,000.00 |
| Sold on Exit | No |
| Description of Works | Office to residential conversion on upper floors, and retention of the downstairs commercial - included a basement dig and 2 storey extension. |

Development Appraisal

Property

10 Kings Road, York, YO1 1ET

Property Type: Residential

Area

Acquisition Area (sq.ft):

Build Area (sq.ft): 6,000

Sales Area (sq.ft): 6000

Sales Area / GIA  (Commercial, sq.ft): 0

Costs

| Purchase Costs |  |
| --- | --- |
| Purchase Price | £1,000,000.00 |
| SDLT | £0.00 |
| Agent Fees | £0.00 |
| Legal Fees | £0.00 |
| Other Fees | £100,000.00 |
| Total Original Purchase Costs | £1,100,000.00 |
| Do you own the property | No |

| Build Costs |  |
| --- | --- |
| Build Costs | £1,000,000.00 |
| Contingency | £75,000.00 |
| Professional Costs & Charges | £100,000.00 |
| Total Build Costs | £1,175,000.00 |

| Sales & Costs |  |
| --- | --- |
| GDV | £3,500,000.00 |
| Marketing Costs | £ 10,000.00 |
| Agent Fees | £ 35,000.00 |
| Legal Fees | £ 10,000.00 |
| Total Sales Costs | £ 55,000.00 |
| NDV | £3,445,000.00 |

Summary

| Purchase Price | £1,000,000.00 |
| --- | --- |
| Total Build Costs | £1,175,000.00 |
| GDV | £3,500,000.00 |
| Loan Term Requested (months) | 18 |
| Build Term (months) | 12 |

Schedule

Houses

| Plot Number | Description | Bedrooms | Bathrooms | Area (sq.ft) | Tenure | Sales Price |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Detached house | 4 | 3 | 1,800 | Freehold | £1,000,000.00 |
| 2 | Semi-detached house | 3 | 2 | 1,200 | Freehold | £ 750,000.00 |
| 3 | Semi-detached house | 3 | 2 | 1,200 | Freehold | £ 750,000.00 |
| 4 | Detached house | 4 | 3 | 1,800 | Freehold | £1,000,000.00 |
|  |  |  | TOTAL | 6,000 |  | £3,500,000.00 |

GDVs

| Commercial GDV | House GDV | Flats GDV | Parking GDV | Total GDV |
| --- | --- | --- | --- | --- |
| £0.00 | £3,500,000.00 | £0.00 | £0.00 | £3,500,000.00 |

Planning

Link to planning decision notice or Planning application

https://publicaccess.tameside.gov.uk/online-applications/simpleSearchResults.do?action=firstPage

Planning description

We purchased the site with outline planning 6 months ago, with a bridging loan. We have now dealt with all reserved matters, and have detailed planning permission for 4 x 3 & 4 bed houses.

Professional Team

| Team Role | Name | Email | Website | Worked With Before | Previous Projects |
| --- | --- | --- | --- | --- | --- |
| Architect | Jane Doe | jane@jdarchitects.com | https://janedoearchitects.com | Yes | Worked with them on our project in Soho Square |
| Main Contractor | JS Build & Design | john@jsdandb.com | https://jsbuildanddesign.com | Yes | Project on Soho Square |
| Structural Engineer | R Charles | info@rcharles.com | http://www.rcharles.com/ | Yes | Project in Soho Square |

COMPARABLE PROPERTIES

Example 1

Property Type: 4 bed detached house

URL: https://www.rightmove.co.uk/properties/118409864#/?channel=RES_BUY

Value: £1,100,000.00

Is this a good comparable? Yes

Why is this a good/bad comparable: It is a very similar spec and layout to our property and is in the same side of the road - south-facing

Example 2

Property Type: 4 bed detached house

URL: https://www.rightmove.co.uk/properties/119098043#/?channel=RES_BUY

Value: £1,150,000.00

Is this a good comparable? Yes

Why is this a good/bad comparable: Similar property - different street

Assets and Liabilities – John Doe

Assets

| Property Assets |  |
| --- | --- |
| Residential Properties |  |
| 32 Brookside Road | £900,000.00 |
| Buy to let (BTL) Properties |  |
| 10 Brookside Road | £850,000.00 |
| 95 Flowerhill Way | £600,000.00 |
| Commercial Properties |  |
| 1 King Street, York | £2,300,000.00 |
| Overseas Properties | £0 |
| TOTAL | £4,650,000.00 |

| Other Assets |  |
| --- | --- |
| Cash/Deposits |  |
| Savings | £1,000,000.00 |
| Stocks & Shares |  |
| Barclays bank | £450,000.00 |
| Business equipment, vehicles, art, other | £0 |
| TOTAL | £1,450,000.00 |
| TOTAL ASSETS | £6,100,000.00 |

Liabilities

| Property Liabilities |  |
| --- | --- |
| Address | Value |
| Residential Property Loans |  |
| 32 Brookside | £250,000.00 |
| TOTAL | £250,000.00 |

| Other Liabilities |  |
| --- | --- |
| Leasing, overdraft, other loans | £0.00 |
| TOTAL | £0.00 |

| TOTAL LIABILITIES | £250,000.00 |
| --- | --- |

| NET ASSETS | £5,850,000.00 |
| --- | --- |

Outstanding Personal Guarantees

| Lender | PG Amount Outstanding | Start Date | Expected End Date |
| --- | --- | --- | --- |
| Paragon | £400,000.00 | 2021-12-01 | 2023-03-31 |
| Total Outstanding Personal Guarantees | £400,000.00 |  |  |

Further supporting information

| Contact details for site access | Selling agents :- Carter Jonas York office 82 Micklegate York YO1 6LF. 01904 558200 |
| --- | --- |
| Nationality | British |
| If not UK national – visa status | N/A |
| If not UK national – years in UK | N/A |
| UK resident | YES |
| Bank Details - Company | Metro Bank One Southampton Row, London WC1B 5HA Sort Code 23-05-80 Account no. 33742813 |
| Bank Details - Personal | Barclays Bank Enfield Town Sort Code 20-29-77 Account no. 90346139 |
| Solicitor’s details | - John Nelmes – Fieldfisher solicitors - Riverbank House, 2 Swan Lane, London EC4R 3TT - john.nelmes@fieldfisher.com - 0330460 6885 |
| Accountant’s details | - Kevin Hayman – King & Taylor Accountants - Joynes House, New Road, Gravesend DA11 0AT - 01474 569777 |

Appendix

Image of Property

Location area of property – Google Maps